## Sheet1
OPEN CONTRACTING DATA STANDARD (OCDS) TEMPLATE FOR PUBLISHING AWARDED CONTRACTS ON THE WEBSITE
S/N | Project | Cost | Budget Amount | Rationale/Needs Assesment | Location | Procurement Category | Procurement Method Used | Date of Advert | Date of Bids Opening | Award Criteria | Completion Period/Duration | Contract BoQ | Date of Award | Date for Signing of contract | Commencement date | Final Date of Completion | Name of Contractor | Address of Contractor | Tel. No | Email | Projects Photographs | Project Funding | Project Status
1 | Renovation Wroks at Gen. Hospital Kachia | 84467027.04 | 1052949448.95 | Yes | Kachia LG | NCB (Goods) | Selective Tendering |  | 2019-03-19 | RDPC | 12 Weeks | Yes | 2019-03-20 | 2019-03-28 | 15th April 19 | 8th July 19 | Zahama Ten Global Ventures Ltd | #6 Club Road, Hamdala Hotel Kaduna | 08064695550 | kabirsani28@gmail.com |  | KDSG | 35%
2 | Procurement of Dental Equipment at Kaduna State Dental Centre, KASU | 24000000 | 1052949448.95 | Yes | KASU, Kaduna | NCB (Goods) | Selective Tendering |  | 2019-01-19 | RDPC | 10 Weeks | Yes | 2019-01-11 | 2019-02-26 | 2019-03-12 | 2019-07-21 | City Shelters & Properties ltd | 15 Freetown Street, Wuse II Abuja |  | citygroupabuja@yahoo.com |  | KDSG | 0%
3 | Const. of Maternity, Lab & X-ray blocks @ MIBA Hospital, S/Gari, Zaria | 118341478.11 | 1052949448.95 | Yes | S/Gari Zaria | NCB (Goods) | Selective Tendering |  |  | RDPC | 16 Weeks | Yes | 2018-12-27 | 2019-01-10 |  | 2019-02-27 | Imsy Ventures Limited | 22 Lateef Jakande Crescent, Gudu District Abuja | 08034021767 | benos.imoisili@yahoo.com |  | KDSG | 0%
4 | Reh. & procurement of Dental Equipment at Dental Centre, Zaria | 29541908.55 | 1052949448.95 | Yes | Zaria | NCB (Goods) | Selective Tendering |  |  | RDPC | 10 Weeks | Yes | 2019-01-08 | 2019-02-26 | 2019-03-12 | 2019-07-21 | Zeallar Solutions Limited | 22 Dibar Street, Okota - Isola, Lagos | 01-7731496 |  |  | KDSG | 10%

## Sheet1 (2)
ANNUAL PROCUREMENT PLAN FOR THE 2017 BUDGETARY YEAR
Ministry of Health and Human Services
S/N | Project Description | BASIC DATA, PROJECT PREPARATION AND DOCUMENTATION |  |  |  |  | His Excellency's Clearance/Approval for the Project | TENDERING (BIDDING) PROCESS |  |  |  | Due Process Compliance Certification | CONTRACT AWARD |  | PROJECT IMPLIMENTATION
|  | Feasibility Studies/Condition Survey (Where Applicable) | Preparation of tender documents (designs and specifications) by Consultants or MDA's | Budgetary Provision in Naira | Estimated Total Cost (ETC) in Naira | Procurement method to be used |  | Advertisement date | Tendering Period (Bidding) | Date of Bids Opening | Bids Evaluation Report & recommendation of the RDPT of the MDA |  | Awarding Authority | Estimated date of Contract Award | Estimated Date for Signing of contract | Estimated Project Commencement date | Completion Period | Estimated Completion Date
These must be thought out by MDA's
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | Upgrading of Lab and the procurement of Containerised Modular TB Lab at Yusuf Dantsoho Memorial Hospital |  | 2017-08-06 | 1466513182.8 | 162239719.95 | Open | [5 empty] | 28 - 31/03/16 | Public Procurement Authority | Just Awarded | 30/1/17 - 15/2/17 | 2017-02-15 | 12 Weeks | 2017-05-17
2 | Construction of ICT Hall at Yusuf Dantsoho Memorial Hospital |  | 2017-08-02 | 1466513182.8 | 14391846 | open | [5 empty] | 28 - 31/03/16 | Public Procurement Authority | 25/04/16 | 26/04/16 | 27/04/16 | 12 Weeks | 20/07/16
1 | Proposed Construction of Visiting Doctor's and Utility Quarters at Yusuf Dantsoho Memorial Hospital (4 Blocks - 8 Units) | 13/01/16 | 2016-08-02 | 36287984.2 | 36101914.36 | Selective Tendering | 11 - 18/02/16 | Invitation to Tender 18 - 29/02/16 | 14 Days (22 - 11/03/16 | 2016-11-03 | 12 Days (11 - 25/03/16) | 28 - 31/03/16 | Public Procurement Authority | 25/04/16 | 26/04/16 | 27/04/16 | 21 Weeks | 14/09/16
Public Procurement Authority
4 | Repairs and Renovation of Accident and Emergency Ward at Doka General Hospital | 2015-10-07 | 2016-08-08 | 1000000000 | 11670592.5 | Selective Tendering | 11 - 18/02/16 | Invitation to Tender 18 - 29/02/16 | 14 Days (22 - 11/03/16 | 2016-11-03 | 12 Days (11 - 25/03/16) | 28 - 31/03/16 | Public Procurement Authority | 25/04/16 | 26/04/16 | 27/04/16 | 8 Weeks | 14/06/16
5 | Completion of 1 No Block of 4No two bedroom doctor's quarters at Sabon Tasha, kaduna | 2015-10-07 | 2016-08-08 | 69923828.42 | 5000000 | Single Source | 11 - 18/02/16 | Invitation to Tender 18 - 29/02/16 | 14 Days (22 - 11/03/16 | 2016-11-03 | 12 Days (11 - 25/03/16) | 28 - 31/03/16 | Public Procurement Authority | 25/04/16 | 26/04/16 | 27/04/16 | 4 Weeks | 25/05/16
Public Procurement Authority
6 | Proposed Repairs and Renovation of Staff Quarters at Dabo Lere General Hospital, Saminaka | 2015-09-11 | 16/02/16 | 1000000000 | 28666424.71 | Selective Tendering | 1 - 7/03/16 | Invitation to Tender (8 - 10-3-2016 | 14 Days (11 - 30/03/16 | 30/03/16 | 12 Days (30 - 15/04/16 | 18 - 20/04/16 | Public Procurement Authority | 25/05/16 | 26/05/16 | 27/05/16 | 20 Weeks | 14/10/16
7 | Landscapiing and Beautification of Major Generals Hospitals across the state | 2015-09-11 | 16/02/16 | 20240000 | 19985962.8 | Selective Tendering | 1 - 7/03/16 | Invitation to Tender (8 - 10-3-2016 | 14 Days (11 - 30/03/16 | 30/03/16 | 12 Days (30 - 15/04/16 | 18 - 20/04/16 | Public Procurement Authority | 25/05/16 | 26/05/16 | 27/05/16 | 18 Weeks | 30/09/16
8 | Establishment of Kaduna State Emergency Medical Services to increase access to Health Care | 2015-09-11 | 16/02/16 | 62900000 | 62899450 | Selective Tendering | 1 - 7/03/16 | Invitation to Tender (8 - 10-3-2016 | 14 Days (11 - 30/03/16 | 30/03/16 | 12 Days (30 - 15/04/16 | 18 - 20/04/16 | Public Procurement Authority | 25/05/16 | 26/05/16 | 27/05/16 | 5 Weeks | 2016-01-07
9 | Procurement of 6No Ambulances for 6 Major General Hospitals | 2015-12-11 | 16/02/16 | 54000000 | 53998792 | Selective Tendering | 1 - 7/03/16 | Invitation to Tender (8 - 10-3-2016 | 14 Days (11 - 30/03/16 | 30/03/16 | 12 Days (30 - 15/04/16 | 18 - 20/04/16 | Public Procurement Authority | 25/05/16 | 26/05/16 | 27/05/16 | 9 Weeks | 29/07/16
Public Procurement Authority
10 | Proposed Renovation of Storm damage at Jibrin Mai Gwari General Hospital, Birnin Gwari | 2015-08-06 | 25/02/16 | 1000000000 | 29261140.97 | Selective Tendering | 10 - 17/03/16 | Invitation to Tender (18 - 15/03/16 | 14 Days (16 - 6/04/16) | 2016-06-04 | 12 Days (6 - 22/04/16) | 25 - 27/04/16 | Public Procurement Authority | 2016-01-06 | 2016-02-06 | 2016-06-06 | 20 Weeks | 24/10/16
11 | Repairs and Renovation of Kaduna State Dental Clinic | 18-7-2015 | 25/02/16 | 1000000000 | 27450948 | Selective Tendering | 10 - 17/03/16 | Invitation to Tender (18 - 15/03/16 | 14 Days (16 - 6/04/16) | 2016-06-04 | 12 Days (6 - 22/04/16) | 25 - 27/04/16 | Public Procurement Authority | 2016-01-06 | 2016-02-06 | 2016-06-06 | 9 Weeks | 2016-08-08
12 | Proposed Construction of Admin Block and Theatre /Repairs and Renovation of General Hospital, Kaura | 2015-08-09 | 25/02/16 | 1000000000 | 67253063.01 | Selective Tendering | 10 - 17/03/16 | Invitation to Tender (18 - 15/03/16 | 14 Days (16 - 6/04/16) | 2016-06-04 | 12 Days (6 - 22/04/16) | 25 - 27/04/16 | Public Procurement Authority | 2016-01-06 | 2016-02-06 | 2016-06-06 | 20 Weeks | 24/10/16
13 | Repairs and Renovation of Storm Damage at Dabo Lere General Hospital, Saminaka | 2015-08-10 | 25/02/16 | 1000000000 | 7046551.35 | Selective Tendering | 10 - 17/03/16 | Invitation to Tender (18 - 15/03/16 | 14 Days (16 - 6/04/16) | 2016-06-04 | 12 Days (6 - 22/04/16) | 25 - 27/04/16 | Public Procurement Authority | 2016-01-06 | 2016-02-06 | 2016-06-06 | 8 Weeks | 2016-01-08
200132412.54